| Tasks | Estimated completion date | Status Update |
| --- | --- | --- |
| 1: Testing the freeze-thaw cycle on enzyme activity -Compare two in-house batches, Thaw from -80, do activity assay, freeze the enzyme for 1 hours and thaw again to do the activity 500 uM NAD, 250 uM p53, 30 min reaction, 10 U/Rxn (4Rxn) 2: Prepare FdL/Honokiol report 3: Repeat the experiment (#2) with p53 (30 min reaction) 3a: 100 uM NAD, 10 uM P53 W/O DMSO, with DMSO, with 10 uM Honokiol (3Rxn) 3b: 100 uM NAD, 50 uM P53 W/O DMSO, with DMSO, with 10 uM Honokiol (3Rxn) 3c: 100 uM NAD, 100 uM P53 W/O DMSO, with DMSO, with 10 uM Honokiol (3Rxn) | 6-6-2016 | Done Done |
| Endpoint assays (two time points; 5 and 30 min, 10U/rxn) 4: Assay non-saturating NAD & saturating peptide 4a: 100 uM NAD, 600 uM p53, 1% DMSO (2rxn) 4b: 100 uM NAD, 600 uM p53, 10 uM Honokiol (2rxn) 5: Assay non-saturating peptide & saturating NAD 5a: 2 mM NAD, 50 uM p53, 1% DMSO (2rxn) 5b: 2 mM NAD, 50 uM p53, 10 uM Honokiol (2rxn) | 6-10-2016 | Done |
| Endpoint assays (two time points; 5 and 30 min, 10U/rxn) 6: Assay non-saturating NAD & saturating peptide 6a: 100 uM NAD, 600 uM AseCS2, 1% DMSO (2rxn) 6b: 100 uM NAD, 600 uM AseCS2, 10 uM Honokiol (2rxn) 7: Assay non-saturating peptide & saturating NAD 7a: 2 mM NAD, 50 uM AseCS2, 1% DMSO (2rxn) 7b: 2 mM NAD, 50 uM AseCS2, 10 uM Honokiol (2rxn) | 6-16-2016 | Done |
| 8: Assay with different concentration of AceCS2 peptide Saturating NAD+ and 1, 5, and 10 uM AceCS2 peptide (12 Rxn) | 6-24-2016 | Done (further optimization is on hold, plan is posted on wiki) |
| 9: Assay of Sirt3 with MnSOD-K122 peptide, Enzo Sirt3 5U/Rxn 9a) Saturating NAD with 5 and 10 uM K-122 MnSOD 9b) Un-saturating NAD (100 uM) with 50 and 250 uM K-122 MnSOD If 5U/rxn doesn’t work, then move to- Assay of Sirt3 with MnSOD-K122 peptide, Enzo Sirt3 10U/Rxn 9c) Saturating NAD with 5 and 10 uM K-122 MnSOD 9d) Un-saturating NAD (100 uM) with 50 and 250 uM K-122 MnSOD | 7-5-2016 | Done |
| 10: Assay with Different concentration of Honokiol Enzo 5U/Rxn for 30 min. Range of Honokiol will be used: 10, 50, 100, 200 uM 2mM NAD, and 10 uM K-122 MnSOD 10a) with DMSO and with Honokiol (6 Rxn) 100 uM NAD, 250 uM K122 MnSOD 10b) with DMSO and with Honokiol (6 Rxn) | 7-11-2016 |  |
| Initial rate with 5% DMSO (K-122-MnSOD and in-house enzyme) 11: Initial rate with saturating peptide 11a: with 5% DMSO (42 rxn) 600 uM K-122 MnSOD 100, 200, 400, 600, 800, 1200, 2000 uM NAD Time: 5, 10, 20, 40, 80, 160 min 11b: with Honokiol (concentration of HNK TBD, based on #10) 600 uM K-122 MnSOD 100, 200, 400, 600, 800, 1200, 2000 uM NAD Time: 5, 10, 20, 40, 80, 160 min 12: Initial rate ; saturating NAD 12a: 2 mM NAD with 5% DMSO (42 rxn) 25, 50, 100, 300, 500, 600, 1000 uM peptide Time: 5, 10, 20, 40, 80, 160 min 12b: with Honokiol (concentration of HNK TBD, based on #10) 2 mM NAD 25, 50, 100, 300, 500, 600, 1000 uM peptide Time: 5, 10, 20, 40, 80, 160 min | 7-20-2016 7-29-2016 (with one [HNK], 42 rxn) 8-9-2016 8-18-2016 (with one [HNK], 42 rxn) | It will be advisable to do saturating peptide initial rate expts (no honokiol) before saturating nad. Also it may be advisable to do initial rate in presence of honokiol and saturating peptide directly after the above. |