| Schedule revised (8-3-2016): 1: Start date is pending approval of this schedule; 2: Minimum amount of in-house Sirt3 needed 3120 uL (3500 ul) of 1.5U/ul. I want to have some extra Sirt3 at my disposal, just in case I need it during this period. 3: All inter-day repeats. |  |  |
| --- | --- | --- |
| Task | Expected completion date | Remarks/Status |
| PMC-AU1: Determine detectability limit for c-K122-MnSOD peptide (Total: 20 samples) - 0.625, 1.25, 2.5, 5, 10 uM of Non-Ac-K122 (5 samples) - Repeat one time (with same sample; intra-day) (5 samples) - Run #a from fresh sample (5 samples) - Repeat one time #c (5 samples) | Completed by 08-12-16 One HPLC | AU46 Completed, submitted on 8-12-2016 |
| PMC-AU2: Estimate saturating [NAD] Total: 30 samples - Three reactions with 1, 2, and 3 mM NAD and 600 uM K122-MnSOD, 5U/rxn, 30 min (6 samples) - One repeat #a (6 samples) - Saturating [NAD] (from #a), 5% DMSO) + [peptide] (from PMC-AU1) to see if other components affect the detection limit. Time: 5 and 30 min, 5U and 10U/Rxn (6 samples) - 2x Repeat #c (12 samples) | Expected to complete by 08-16-2016 One HPLC, [a, b: duplicate, c,d: triplicate] | AU47 In-house Enzyme: 30 x 10U = 300U Stock: 1.5U/ul Needed: 200 uL |
| PMC-AU3: See the minimum [NAD], and saturating Peptide (600 uM) can be used (endpoint, 30 min, 60 min). All reactions should be done in 5% DMSO (Total 12 samples) - 50 uM NAD, 600 uM K122-MnSOD (2 samples) - 75 uM NAD, 600 uM K122-MnSOD (2 samples) - 100 uM NAD, 600 uM K122-MnSOD (2 samples) - One time repeat (6 samples) | Expected to complete by 08-19-2016 One HPLC, Duplicate | AU48 In-house Enzyme: 12 x 10U = 120U Stock: 1.5U/ul Needed: 80 uL |
| PMC-AU4: HNK dose response, [HNK] = 0, 1, 5, 10, 25, 50, 100, 200 uM, Time = TBD (48 Samples) - Minimum [NAD], and 600 uM K122 (8 samples) - Saturating [NAD] , minimum K122 (8 samples) - Two time repeat of each 1 and 2 (32 samples) Edit: 8-22-2016: Time 30 min but may need to do one more time depending upon results. | Expected to complete by 08-30-2016 One HPLC, Triplicate | AU49 In-house Enzyme: 48 x 5U = 240U Stock: 1.5U/ul Needed: 160 uL |
| PMC-AU5: Determine Km NAD with and w/o 5% DMSO, with Honokiol (432 samples), does not include blanks(6): - Saturating K-122 MnSOD (600 uM), [NAD] = 25, 50, 100, 250, 500, 1000, 2000, 3000 uM - Time: 10, 20, 30, 40, 80, 120 min (48 samples) - Same reactions with 5% DMSO (48 samples) - Same reactions with 200 uM Honokiol in 5% DMSO (48 samples) - Two repeats (1,2,3) above to confirm (288 samples) | Starting from 9-26-2016 Expected to complete by 11-16-2016 Three HPLC, Triplicate | AU50 In-house Enzyme: 378 x 5U = 2160U Stock: 1.5U/ul Needed: 1440 uL |

Footnote:

- For duplication, two HPLC will be used and the completion date is 10.3.2016. As suggested triplicate will be done either in house at later time or by CRO. Since the duplication/ triplication will be run parallel on the 2nd/3rd HPLC, the total time will not be reduced significantly.

- In the revised AU/XG schedules, there is no conflict of usage of HPLC. AU will use one HPLC for expt. PMC-AU4, which aligned to XG’s.

- Experiment AU2 a, b, are for saturating NAD determination. And c, d is to see if selected condition gives quantifiable product with saturating [NAD] and minimum peptide conc chosen.

- For initial rate, note change in concentration and time of the reaction.

- In a set of the reaction, the reaction will be carried out together and 50 uL aliquot will be take out at specified time and quenched with 2 % TFA.

- Multiple blanks will be added/done during the reaction, and they will be run on HPLC to see the quality of the data.